## W1
PROJECT REPORT
Group | SEP490_G5
Week | 11/05/2026-17/05/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Feature development | Phat | Done | 2 commits this week
2 | General maintenance | Phat | Done | 1 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | No blocking issue raised this week |  | Closed
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Clinical EMR service | Phat | 24/05/2026 | Planned for week 2
2 | User & role management | Khoa | 24/05/2026 | Planned for week 2
3 | Specialty catalog | Chinh | 24/05/2026 | Planned for week 2
4 | Doctor scheduling | Phat | 24/05/2026 | Planned for week 2
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Next deliverable: Report 1 - Project Plan | All members | 22/05/2026 | Due in 5 day(s)
Note on D5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on D11: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W2
PROJECT REPORT
Group | SEP490_G5
Week | 18/05/2026-24/05/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Clinical EMR service | Phat | Done | 20 commits this week
2 | User & role management | Khoa | Done | 20 commits this week
3 | Specialty catalog | Chinh | Done | 16 commits this week
4 | Doctor scheduling | Phat | Done | 12 commits this week
5 | Appointment booking | Nhan | Done | 10 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | No blocking issue raised this week |  | Closed
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | User & role management | Khoa | 31/05/2026 | Planned for week 3
2 | AI services (KYC OCR, booking assistant) | Nhan | 31/05/2026 | Planned for week 3
3 | Feature development | Phat | 31/05/2026 | Planned for week 3
4 | TLS certificates | Phat | 31/05/2026 | Planned for week 3
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Report 1 - Project Plan submitted | All members | 22/05/2026 | Deliverable milestone
2 | Next deliverable: Report 2 - Requirement Elicitation | All members | 05/06/2026 | Due in 12 day(s)

## W3
PROJECT REPORT
Group | SEP490_G5
Week | 25/05/2026-31/05/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | User & role management | Khoa | Done | 24 commits this week
2 | AI services (KYC OCR, booking assistant) | Nhan | Done | 11 commits this week
3 | Feature development | Phat | Done | 8 commits this week
4 | TLS certificates | Phat | Done | 7 commits this week
5 | Landing page | Khoa | Done | 4 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | No blocking issue raised this week |  | Closed
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | KYC identity verification | Nhan | 07/06/2026 | Planned for week 4
2 | Web frontend | Nhan | 07/06/2026 | Planned for week 4
3 | Google OAuth sign-in | Khoa | 07/06/2026 | Planned for week 4
4 | IAM service | Nhan | 07/06/2026 | Planned for week 4
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Next deliverable: Report 2 - Requirement Elicitation | All members | 05/06/2026 | Due in 5 day(s)

## W4
PROJECT REPORT
Group | SEP490_G5
Week | 01/06/2026-07/06/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | KYC identity verification | Nhan | Done | 20 commits this week
2 | Web frontend | Nhan | Done | 12 commits this week
3 | Google OAuth sign-in | Khoa | Done | 12 commits this week
4 | IAM service | Nhan | Done | 8 commits this week
5 | API documentation | Nhan | Done | 8 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Defects raised in KYC identity verification | Nhan | Closed | 8 fix commits merged
2 | Defects raised in IAM service | Nhan | Closed | 4 fix commits merged
3 | Defects raised in Clinical EMR service | Phat | Closed | 4 fix commits merged
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Web frontend | Phat | 14/06/2026 | Planned for week 5
2 | AI services (KYC OCR, booking assistant) | Nhan | 14/06/2026 | Planned for week 5
3 | KYC identity verification | Nhan | 14/06/2026 | Planned for week 5
4 | Appointment booking | Nhan | 14/06/2026 | Planned for week 5
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Report 2 - Requirement Elicitation submitted | All members | 05/06/2026 | Deliverable milestone
2 | Next deliverable: Report 3 - Software Requirement Specification | All members | 19/06/2026 | Due in 12 day(s)

## W5
PROJECT REPORT
Group | SEP490_G5
Week | 08/06/2026-14/06/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Web frontend | Phat | Done | 117 commits this week
2 | AI services (KYC OCR, booking assistant) | Nhan | Done | 72 commits this week
3 | KYC identity verification | Nhan | Done | 32 commits this week
4 | Appointment booking | Nhan | Done | 20 commits this week
5 | Backend services | Phat | Done | 16 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Defects raised in AI services (KYC OCR, booking assistant) | Nhan | Closed | 16 fix commits merged
2 | Defects raised in Web frontend | Phat | Closed | 12 fix commits merged
3 | Defects raised in Appointment booking | Nhan | Closed | 8 fix commits merged
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | AI services (KYC OCR, booking assistant) | Nhan | 21/06/2026 | Planned for week 6
2 | Feature development | Phat | 21/06/2026 | Planned for week 6
3 | Backend services | Phat | 21/06/2026 | Planned for week 6
4 | Feature revision | Nhan | 21/06/2026 | Planned for week 6
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Next deliverable: Report 3 - Software Requirement Specification | All members | 19/06/2026 | Due in 5 day(s)

## W6
PROJECT REPORT
Group | SEP490_G5
Week | 15/06/2026-21/06/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | AI services (KYC OCR, booking assistant) | Nhan | Done | 192 commits this week
2 | Feature development | Phat | Done | 89 commits this week
3 | Backend services | Phat | Done | 40 commits this week
4 | Feature revision | Nhan | Done | 24 commits this week
5 | Authentication | Khoa | Done | 8 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Defects raised in AI services (KYC OCR, booking assistant) | Nhan | Closed | 48 fix commits merged
2 | Defects raised in Feature revision | Nhan | Closed | 16 fix commits merged
3 | Defects raised in Kyc&routing | Khoa | Closed | 4 fix commits merged
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | AI services (KYC OCR, booking assistant) | Nhan | 28/06/2026 | Planned for week 7
2 | Clinical examination workflow | Nhan | 28/06/2026 | Planned for week 7
3 | Web frontend | Nhan | 28/06/2026 | Planned for week 7
4 | Booking flow | Nhan | 28/06/2026 | Planned for week 7
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Report 3 - Software Requirement Specification submitted | All members | 19/06/2026 | Deliverable milestone
2 | Next deliverable: Report 4 - Software Design Document | All members | 03/07/2026 | Due in 12 day(s)

## W7
PROJECT REPORT
Group | SEP490_G5
Week | 22/06/2026-28/06/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | AI services (KYC OCR, booking assistant) | Nhan | Done | 76 commits this week
2 | Clinical examination workflow | Nhan | Done | 72 commits this week
3 | Web frontend | Nhan | Done | 32 commits this week
4 | Booking flow | Nhan | Done | 32 commits this week
5 | Chat assistant | Nhan | Done | 8 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Defects raised in Clinical examination workflow | Nhan | Closed | 56 fix commits merged
2 | Defects raised in Booking flow | Nhan | Closed | 20 fix commits merged
3 | Defects raised in Web frontend | Nhan | Closed | 17 fix commits merged
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Clinical examination workflow | Nhan | 05/07/2026 | Planned for week 8
2 | Clinical EMR service | Phat | 05/07/2026 | Planned for week 8
3 | Web frontend | Nhan | 05/07/2026 | Planned for week 8
4 | Project documentation | Phat | 05/07/2026 | Planned for week 8
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Next deliverable: Report 4 - Software Design Document | All members | 03/07/2026 | Due in 5 day(s)

## W8
PROJECT REPORT
Group | SEP490_G5
Week | 29/06/2026-05/07/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Clinical examination workflow | Nhan | Done | 162 commits this week
2 | Clinical EMR service | Phat | Done | 34 commits this week
3 | Web frontend | Nhan | Done | 33 commits this week
4 | Project documentation | Phat | Done | 15 commits this week
5 | API gateway | Phat | Done | 14 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Defects raised in Clinical examination workflow | Nhan | Closed | 108 fix commits merged
2 | Defects raised in Web frontend | Nhan | Closed | 27 fix commits merged
3 | Defects raised in Clinical EMR service | Phat | Closed | 9 fix commits merged
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Web frontend | Khoa | 12/07/2026 | Planned for week 9
2 | End-to-end flow verification | Khoa | 12/07/2026 | Planned for week 9
3 | Container setup | Phat | 12/07/2026 | Planned for week 9
4 | Clinical EMR service | Khoa | 12/07/2026 | Planned for week 9
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Report 4 - Software Design Document submitted | All members | 03/07/2026 | Deliverable milestone
2 | Next deliverable: Report 5 - Test Report & Unit Test | All members | 17/07/2026 | Due in 12 day(s)

## W9
PROJECT REPORT
Group | SEP490_G5
Week | 06/07/2026-12/07/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Web frontend | Khoa | Done | 20 commits this week
2 | End-to-end flow verification | Khoa | Done | 8 commits this week
3 | Container setup | Phat | Done | 4 commits this week
4 | Clinical EMR service | Khoa | Done | 4 commits this week
5 | Database schema | Khoa | Done | 2 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Defects raised in Web frontend | Khoa | Closed | 8 fix commits merged
2 | Defects raised in Clinical EMR service | Khoa | Closed | 4 fix commits merged
3 | Defects raised in Payments | Khoa | Closed | 2 fix commits merged
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Web frontend | Chinh | 19/07/2026 | Planned for week 10
2 | Housekeeping | Phat | 19/07/2026 | Planned for week 10
3 | Code quality | Phat | 19/07/2026 | Planned for week 10
4 | Cross-cutting fixes | Khoa | 19/07/2026 | Planned for week 10
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Next deliverable: Report 5 - Test Report & Unit Test | All members | 17/07/2026 | Due in 5 day(s)

## W10
PROJECT REPORT
Group | SEP490_G5
Week | 13/07/2026-19/07/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Web frontend | Chinh | Done | 24 commits this week
2 | Housekeeping | Phat | Done | 3 commits this week
3 | Code quality | Phat | Done | 2 commits this week
4 | Cross-cutting fixes | Khoa | Done | 2 commits this week
5 | Demo preparation | Khoa | Done | 2 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Defects raised in Web frontend | Chinh | Closed | 6 fix commits merged
2 | Defects raised in Demo preparation | Khoa | Closed | 2 fix commits merged
3 | Defects raised in Code quality | Phat | Closed | 1 fix commit merged
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Web frontend | Khoa | 26/07/2026 | Planned for week 11
2 | Web UI revision | Phat | 26/07/2026 | Planned for week 11
3 | CI/CD pipeline | Phat | 26/07/2026 | Planned for week 11
4 | IAM service | Khoa | 26/07/2026 | Planned for week 11
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Report 5 - Test Report & Unit Test submitted | All members | 17/07/2026 | Deliverable milestone
2 | Next deliverable: Report 6 - Installation & User Guide | All members | 31/07/2026 | Due in 12 day(s)

## W11
PROJECT REPORT
Group | SEP490_G5
Week | 20/07/2026-26/07/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Web frontend | Khoa | Done | 55 commits this week
2 | Web UI revision | Phat | Done | 18 commits this week
3 | CI/CD pipeline | Phat | Done | 18 commits this week
4 | IAM service | Khoa | Done | 15 commits this week
5 | Database schema | Phat | Done | 15 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Defects raised in Web frontend | Khoa | Closed | 20 fix commits merged
2 | Defects raised in IAM service | Khoa | Closed | 10 fix commits merged
3 | Defects raised in CI/CD pipeline | Phat | Closed | 6 fix commits merged
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Bilingual support (VI/EN) | Khoa | 02/08/2026 | Planned for week 12
2 | Web frontend | Khoa | 02/08/2026 | Planned for week 12
3 | Incremental updates | Phat | 02/08/2026 | Planned for week 12
4 | Appointment booking | Khoa | 02/08/2026 | Planned for week 12
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Next deliverable: Report 6 - Installation & User Guide | All members | 31/07/2026 | Due in 5 day(s)

## W12
PROJECT REPORT
Group | SEP490_G5
Week | 27/07/2026-02/08/2026
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
1 | Bilingual support (VI/EN) | Khoa | In Progress | 28 commits this week
2 | Web frontend | Khoa | In Progress | 21 commits this week
3 | Incremental updates | Phat | In Progress | 21 commits this week
4 | Appointment booking | Khoa | In Progress | 14 commits this week
5 | Project documentation | Phat | In Progress | 11 commits this week
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
1 | Defects raised in Web frontend | Khoa | In Progress | 3 fix commits merged
2 | Defects raised in Seed data | Nhan | In Progress | 3 fix commits merged
3 | Defects raised in Core modules | Nhan | In Progress | 3 fix commits merged
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
1 | Report 7 - Final Report | All members | 14/08/2026 | Remaining deliverable
IV. Other Project Matters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes
1 | Report 6 - Installation & User Guide submitted | All members | 31/07/2026 | Deliverable milestone
2 | Next deliverable: Report 7 - Final Report | All members | 14/08/2026 | Due in 12 day(s)