## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
0 | Landing Page | Authentication Management | Simple | Public home page introducing the clinic network and entry points to sign in or register. | Iteration 1 | Done
1 | Login | Authentication Management | Simple | Authenticate by email/phone and password and grant role-based access to the system. | Iteration 1 | Done
2 | Register | Authentication Management | Simple | Create a patient account with email/phone, password and OTP verification. | Iteration 1 | Done
3 | Forgot Password | Authentication Management | Simple | Request a password-reset code for the account email or phone. | Iteration 1 | Done
4 | Reset Password | Authentication Management | Simple | Verify the reset code and set a new password. | Iteration 3 | Done
5 | Google Sign-in | Authentication Management | Simple | Complete Google OAuth 2.0 sign-in and link the external identity to an account. | Iteration 2 | Done
6 | Google OAuth Callback | Authentication Management | Simple | Consume the authorization code returned by Google and establish the session. | Iteration 2 | Done
7 | Unauthorized | Authentication Management | Simple | Inform the signed-in user that their role may not access the requested screen. | Iteration 1 | Done
8 | Dashboard | Performance Management | Complex | Role-resolved landing workspace showing the operational summary for the signed-in user. | Iteration 1 | Done
9 | Doctor Dashboard | Performance Management | Simple | Clinical workspace: today's appointments, assigned patients and open examinations. | Iteration 3 | Done
10 | Patient Dashboard | Performance Management | Simple | Patient workspace: upcoming appointments, prescriptions and payment status. | Iteration 3 | Done
11 | Profile Page | User Management | Simple | View and update personal profile information, avatar and password. | Iteration 1 | Done
12 | Booking Assistant | Appointment Management | Complex | AI chat assistant that books and looks up appointments; available as a floating bubble across the app. | Iteration 3 | Done
13 | Appointment List | Appointment Management | Medium | Browse and filter appointments between patients and clinics. | Iteration 1 | Done
14 | Create Appointment | Appointment Management | Complex | Create an appointment by clinic, specialty or doctor and reserve the slot. | Iteration 1 | Done
15 | Appointment Detail | Appointment Management | Complex | Show one appointment with its status history, payment state and clinical links. | Iteration 1 | Done
16 | Update Appointment | Appointment Management | Medium | Modify appointment details, or request/confirm cancellation, and notify related parties. | Iteration 1 | Done
17 | Payment | Appointment Management | Complex | Process the appointment payment through the VNPay integration. | Iteration 1 | Done
18 | Payment Result | Appointment Management | Simple | Reconcile the VNPay callback and display the settled payment outcome. | Iteration 1 | Done
19 | Patient Directory | Patient Management | Medium | Browse and search the patient directory. | Iteration 1 | Done
20 | Add Patient Profile | Patient Management | Medium | Register a new patient profile with demographics and contact details. | Iteration 1 | Done
21 | Patient Profile | Patient Management | Complex | Show one patient with medical history, records, treatment history and representatives. | Iteration 1 | Done
22 | Update Patient Profile | Patient Management | Medium | Edit demographic and contact information of an existing patient. | Iteration 1 | Done
23 | Patient Images | Patient Management | Medium | Browse and attach dental images belonging to one patient. | Iteration 1 | Done
24 | Create Medical Record | Patient Management | Medium | Create a visit-level medical record linked to patient, clinic, doctor and appointment. | Iteration 1 | Done
25 | Medical Record Detail | Patient Management | Complex | Open one medical record with its versions, amendments, attachments and export action. | Iteration 1 | Done
26 | Examination List | Clinic Examination | Medium | Browse clinical examination sessions by clinic, doctor and status. | Iteration 2 | Done
27 | Create Examination | Clinic Examination | Medium | Open a new examination session for a patient from an appointment. | Iteration 2 | Done
28 | Examination Detail | Clinic Examination | Complex | Record symptoms, diagnoses, dental chart, treatment plan, prescription and clinical orders; finalize the session. | Iteration 2 | Done
29 | Dental Image Library | Dental Imaging | Complex | Browse, filter, upload and annotate dental images (X-ray, CBCT, endodontic) across patients. | Iteration 3 | Done
30 | Prescription List | Clinic Examination | Simple | Browse issued prescriptions for the signed-in patient or treating doctor. | Iteration 4 | Done
31 | Clinic Page | Clinic Management | Medium | Display the clinic network with overview information and operational details. | Iteration 1 | Done
32 | Create Clinic | Clinic Management | Medium | Register a new clinic branch. | Iteration 1 | Done
33 | Clinic Detail | Clinic Management | Complex | Show clinic profile, contact, specialties, treatment rooms and offered services. | Iteration 1 | Done
34 | Update Clinic | Clinic Management | Medium | Update clinic information, treatment rooms and configuration data. | Iteration 1 | Done
35 | Service | Service Catalog Management | Medium | Manage the dental service catalog and per-clinic availability and pricing. | Iteration 1 | Done
36 | Add Service | Service Catalog Management | Medium | Add a service to the catalog with category, duration and base price. | Iteration 1 | Done
37 | Update Service | Service Catalog Management | Medium | Update service definition, duration and base price. | Iteration 1 | Done
38 | Specialty | Service Catalog Management | Simple | Manage the clinical specialty catalog and its clinic assignments. | Iteration 1 | Done
39 | Schedule Page | Schedule Management | Medium | Scheduling hub for doctor shifts, leave and work-shift definitions. | Iteration 2 | Done
40 | Doctor Schedule | Schedule Management | Complex | View and manage published doctor schedules by date, clinic and room. | Iteration 1 | Done
41 | Create Schedule | Schedule Management | Medium | Create a doctor schedule entry, unique per doctor, date and shift. | Iteration 2 | Done
42 | Update Schedule | Schedule Management | Medium | Update or delete a schedule entry while it is still mutable, recording the change. | Iteration 3 | Done
43 | Doctor Leave | Schedule Management | Medium | Review and approve doctor leave that blocks availability. | Iteration 1 | Done
44 | Request Leave | Schedule Management | Simple | Submit a leave request for a date range with a reason. | Iteration 2 | Done
45 | Work Shift | Schedule Management | Simple | Maintain the named work-shift definitions used when building schedules. | Iteration 4 | Done
46 | My Schedule | Schedule Management | Medium | Show the signed-in doctor's or nurse's own shifts and request schedule changes. | Iteration 3 | Done
47 | Admin Home | User Management | Simple | Entry point to the administration area. | Iteration 1 | Done
48 | User Management Page | User Management | Complex | Administer user accounts, including ban and unban of policy-violating accounts. | Iteration 1 | Done
49 | Role Page | User Management | Medium | Manage role definitions and the permissions assigned to each role. | Iteration 1 | Done
50 | KYC Management | User Management | Complex | Review submitted identity documents and approve or reject verification. | Iteration 2 | Done
51 | Audit Log | User Management | Medium | Search the tamper-evident log of security and clinical data events. | Iteration 2 | Done
52 | Doctor Performance | Performance Management | Medium | Track doctor productivity and performance indicators and generate reports. | Iteration 3 | Done
53 | Financial Report | Performance Management | Medium | Report clinic revenue and payment settlement over a period. | Iteration 3 | Done
54 | Refund Management | Performance Management | Medium | Review, approve or reject refund requests raised against payments. | Iteration 3 | Done

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 | Web frontend carried the largest share of defect fixes | Rework late in the schedule; UI regressions reaching the demo | High | Khoa | 20/07/2026 | 02/08/2026 | Closed | Raised from the weekly report; fix commits concentrated in the web package in W11-W12
2 | Seed data and database migrations required repeated correction | Unreliable demo data and failed environment resets | Medium | Nhan | 27/07/2026 | 02/08/2026 | Closed | Weekly report W12; resolved by consolidating the seed scripts
3 | Appointment booking defects across scheduling and payment | Double booking or unpaid appointments reaching a clinic | High | Khoa | 20/07/2026 | 02/08/2026 | Closed | Weekly report W11-W12; covered by the no-double-booking exclusion constraints
4 | Four competing use case lists across the documents | Requirements traceability breaks between SRS, SDD and the diagrams | High | ChinhBCCE181383 | 30/07/2026 | 30/07/2026 | Closed | Document change: reconciled to a single backlog of 87 use cases
5 | Blockchain, Hyperledger and IPFS specified as delivered | The SRS commits the team to a dropped feature | High | ChinhBCCE181383 | 01/08/2026 | 01/08/2026 | Closed | Document change: SI-4, R-4, P-4 and DC-3 rewritten around the AI services actually built
6 | Digital signature entity and screens documented but not implemented | Reviewers expect a feature that does not exist | High | ChinhBCCE181383 | 01/08/2026 | 01/08/2026 | Closed | Document change: removed from the entity list, ERD and the SDD database design
7 | Entity attributes drifted from the deployed database | Design documents mislead implementation and testing | High | ChinhBCCE181383 | 01/08/2026 | 01/08/2026 | Closed | Document change: gender corrected to SMALLINT (ISO 5218); column widths refreshed from schema.sql
8 | Screen list omitted twelve implemented screens | Test coverage planned against an incomplete screen list | Medium | ChinhBCCE181383 | 01/08/2026 | 01/08/2026 | Closed | Document change: §3.1.b regenerated from the app router — Register, KYC, audit log, refunds and others added
9 | Section 3.1 numbering skipped letter c | Cross references to §3.1.c point at the wrong section | Low | ChinhBCCE181383 | 01/08/2026 | 01/08/2026 | Closed | Document change: Non-Screen Functions renumbered from d to c
10 | Screen flow diagrams still show a dropped feature | Report 3 contradicts itself between diagram and table | Medium | ChinhBCCE181383 | 01/08/2026 |  | Open | Document change: replacement images generated under docs/diagrams/img; Word images not yet swapped

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Patient Management | Patient Images | ChinhBCCE181383 | No link anywhere in the frontend navigates to /patients/[id]/images; the page is reachable only by typing the URL | Nhan | Open | Found by scanning Link/router.push targets across frontend/web
Patient Management | Medical Record Detail | ChinhBCCE181383 | /patients/[id]/medical-records/[recordId] has no inbound link, although the 'new record' page is linked | Nhan | Open | MedicalRecordList links only to medical-records/new
Schedule Management | Update Schedule | ChinhBCCE181383 | /schedules/doctors/edit/[scheduleId] has no inbound link from the doctor schedule list | Phat | Open | Edit action missing from the schedule table
Clinic Management | Clinic Page | ChinhBCCE181383 | Guest cannot open /clinics or /specialties although UC-23, UC-24 and UC-62 grant Guest those use cases | Khoa | Open | Routes are absent from PUBLIC_ROUTES, so the middleware redirects to login
Appointment Management | Appointment List | ChinhBCCE181383 | AppointmentEntity declares clinic_id NOT NULL but no migration adds the constraint, so the column is nullable | Phat | Open | Entity drift recorded in clinic-service/schema.sql
User Management | Notification Centre | ChinhBCCE181383 | notification_push_subscriptions existed only as a migration and was missing from schema.sql | ChinhBCCE181383 | Closed | Backfilled into database/iam-service/user-service/schema.sql
Appointment Management | Appointment List | ChinhBCCE181383 | appointment_notification_logs.scheduled_for existed only as a migration and was missing from schema.sql | ChinhBCCE181383 | Closed | Backfilled together with the uq_reminder_logs_dedupe index

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
30/07/2026 | Which use case list is authoritative when four versions disagree? | ChinhBCCE181383 | High | Closed | The backlog decides; the count stays at 87 and the other documents follow it
01/08/2026 | Are blockchain and digital signature still in scope? | ChinhBCCE181383 | High | Closed | No — both dropped; the documents now describe the KYC OCR and booking assistant services
01/08/2026 | Should the ERD follow the TypeORM entities or the deployed schema? | ChinhBCCE181383 | Medium | Closed | schema.sql, because it reflects the post-migration database and records entity drift
01/08/2026 | Should Guest be able to browse clinics and specialties without an account? | ChinhBCCE181383 | Medium | Open | The use cases say yes; the middleware currently says no — needs a decision
01/08/2026 | Do password reset screens belong in the signed-in actor flows? | ChinhBCCE181383 | Low | Open | Kept for now, matching the original diagrams; arguably guest-only
01/08/2026 | Should in-page actions such as Ban and Unban be screens or system functions? | ChinhBCCE181383 | Medium | Closed | System functions — they have no route, so they moved to §3.1.c
01/08/2026 | What date should Report 7 carry? | ChinhBCCE181383 | Medium | Closed | 14/08/2026, two weeks after the last development week